## Nonconformity Log
Control Name | Owner | Description | Finding Date | Resolution Date | Status | Comment
NC-1: Legal and regulatory requirements (Clause 4.2 / A.5.31) | Happy Hogan | Legal, statutory and regulatory requirements are not formally identified. The ISMS Scope and Information Security Policy both state that no legal requirements apply, which is incorrect for a US marketing SaaS (for example CAN-SPAM and US state privacy laws). | 20 Mar 2026 |  | Open | Minor nonconformity. Corrective action: establish and maintain a legal requirements register and correct the scope and policy statements.
NC-2: Segregation of duties (A.5.3) | Happy Hogan | Conflicting duties are not formally segregated. In the small team, the same individuals develop, deploy, and review the same systems, with no documented compensating controls or management oversight. | 20 Mar 2026 |  | Open | Minor nonconformity. Corrective action: document segregation-of-duties conflicts and the compensating controls applied.
NC-3: Access rights review (A.5.18 / A.8.2) | Maria Hill | Periodic access reviews are defined as quarterly in policy, but no record of a completed access review for the period was available during the audit. | 20 Mar 2026 |  | Open | Minor nonconformity. Corrective action: perform and record periodic (quarterly) access reviews, including privileged access.

## Opportunities for Improvement
Reference / Area | Owner | Description | Identified Date | Type | Status | Comment / Recommendation
OFI-1: Single-cloud dependency (A.5.30) | Maria Hill | The platform depends entirely on AWS, with no documented provider-failure or exit strategy for prolonged AWS unavailability. | 20 Mar 2026 | OFI | Open | Recommend documenting a continuity and exit plan addressing prolonged loss of the cloud provider.
OFI-2: Training completion tracking (A.6.3) | Happy Hogan | Security awareness training is delivered to staff, but completion is tracked informally with no central record. | 20 Mar 2026 | OFI | Open | Recommend a simple training completion log to evidence coverage across all staff.