## Evidence Register
STARK INDUSTRIES INC. - Audit Fieldwork: Evidence Register
ISO/IEC 27001:2022 Internal Audit - Stage 05. Record of evidence examined during fieldwork.
Audit dates: 16-20 Mar 2026 ¦ Lead Auditor: Nirmay Soni ¦ Version 1.0 ¦ Classification: Internal
Ref | Date | Session / Area | Activity / Evidence Examined | Evidence Type | Source / Owner | Clause / Control | Result
E01 | 16 Mar | Clause 4 & 5 | Reviewed ISMS Scope and Company Profile | Document | Happy Hogan | 4.1 / 4.3 | Conforming
E02 | 16 Mar | Clause 4 & 5 | Reviewed interested-parties and legal-requirements statements | Document | Happy Hogan | 4.2 / A.5.31 | Minor NC
E03 | 16 Mar | Clause 4 & 5 | Reviewed Information Security Policy and leadership commitment | Document | Tony Stark / Happy Hogan | 5.1 / 5.2 | Conforming
E04 | 16 Mar | Clause 4 & 5 | Reviewed ISMS Roles and Responsibilities | Document | Happy Hogan | 5.3 | Conforming
E05 | 16 Mar | Clause 6 | Reviewed Risk Assessment Process and Risk Register | Document | Happy Hogan | 6.1.2 | Conforming
E06 | 16 Mar | Clause 6 | Reviewed Risk Treatment Process and Statement of Applicability | Document | Happy Hogan | 6.1.3 | Conforming
E07 | 16 Mar | Clause 6 | Reviewed ISMS Objectives and KPIs | Document | Happy Hogan | 6.2 | Conforming
E08 | 17 Mar | Clause 7 | Reviewed Competence Records | Record | Happy Hogan | 7.2 | Conforming
E09 | 17 Mar | Clause 7 | Reviewed security awareness and training records | Record | Happy Hogan | A.6.3 | OFI
E10 | 17 Mar | Clause 8 / Tech | Observed secure development workflow (branch protection, code review) | Observation | Natalia Romanoff | A.8.25 / A.8.28 | Conforming
E11 | 17 Mar | Clause 8 / Tech | Reviewed CI/CD pipeline configuration and secrets handling | Configuration | Natalia Romanoff | A.8.4 | Conforming
E12 | 18 Mar | Annex A Tech | Observed AWS IAM and access configuration | Observation | Maria Hill | A.5.18 / A.8.2 | Minor NC
E13 | 18 Mar | Annex A Tech | Reviewed encryption settings (S3, databases) | Configuration | Maria Hill | A.8.24 | Conforming
E14 | 18 Mar | Annex A Tech | Reviewed logging and monitoring (CloudWatch) | Configuration | James Rhodes | A.8.16 | Conforming
E15 | 18 Mar | Annex A Org | Reviewed segregation of duties across the small team | Interview / Document | Happy Hogan | A.5.3 | Minor NC
E16 | 18 Mar | Annex A Org | Reviewed supplier management for AWS | Document | Happy Hogan | A.5.19 / A.5.23 | Conforming
E17 | 19 Mar | Physical / AWS | Reviewed AWS shared-responsibility and physical controls | Document | Maria Hill | A.7 (AWS) | Conforming
E18 | 19 Mar | Physical / AWS | Discussed single-cloud dependency and continuity | Interview | Maria Hill | A.5.30 | OFI
E19 | 19 Mar | Clause 9 & 10 | Reviewed Monitoring, Measurement and KPIs procedure | Document | James Rhodes | 9.1 | Conforming
E20 | 19 Mar | Clause 9 & 10 | Reviewed Internal Audit Programme and this audit's records | Document | Happy Hogan | 9.2 | Conforming
E21 | 19 Mar | Clause 9 & 10 | Reviewed Management Review records | Record | Happy Hogan | 9.3 | Conforming
E22 | 19 Mar | Clause 9 & 10 | Reviewed nonconformity and corrective-action process | Document | Happy Hogan | 10.2 | Conforming

## Interview & Observation Notes
STARK INDUSTRIES INC. - Audit Fieldwork: Interview and Observation Notes
ISO/IEC 27001:2022 Internal Audit - Stage 05. Summary notes from interviews and observations.
Audit dates: 16-20 Mar 2026 ¦ Lead Auditor: Nirmay Soni ¦ Version 1.0 ¦ Classification: Internal
Ref | Date | Auditee | Role | Topic | Notes | Outcome
I01 | 16 Mar | Happy Hogan | Information Security Manager | Context, scope, legal requirements | Confirmed ISMS scope; stated that no legal or regulatory requirements apply to the platform. | Led to NC-1
I02 | 16 Mar | Tony Stark | Chief Executive Officer | Leadership and commitment | Demonstrated commitment, resourcing, and support for security culture. | Conforming
I03 | 16 Mar | Happy Hogan | GRC / ISM | Risk management | Risk methodology applied; risk register maintained with scored risks. | Conforming
I04 | 17 Mar | Happy Hogan | Information Security Manager | Competence and training | Awareness training delivered to staff, but completion is not formally logged. | Led to OFI-2
I05 | 17 Mar | Natalia Romanoff | Software Developer | Secure development | Secure coding, peer code review, and branch protection in place. | Conforming
I06 | 18 Mar | Maria Hill | IT Infrastructure Engineer | Access control | Access is provisioned and restricted; could not show records of periodic access reviews. | Led to NC-3
I07 | 18 Mar | Happy Hogan | Information Security Manager | Segregation of duties | Acknowledged overlapping duties in the small team; no documented compensating controls. | Led to NC-2
I08 | 19 Mar | Maria Hill | IT Infrastructure Engineer | Continuity and cloud dependency | Heavy reliance on AWS; no documented provider-failure or exit plan. | Led to OFI-1
I09 | 19 Mar | James Rhodes | Information Security Analyst | Monitoring and logging | Logging enabled and alerts monitored; incident process understood. | Conforming

## Sampling Record
STARK INDUSTRIES INC. - Audit Fieldwork: Sampling Record
ISO/IEC 27001:2022 Internal Audit - Stage 05. Basis and results of sampling performed.
Audit dates: 16-20 Mar 2026 ¦ Lead Auditor: Nirmay Soni ¦ Version 1.0 ¦ Classification: Internal
Ref | Area / Control | Population | Sample Size | Basis for Selection | Result
SA01 | User access (AWS IAM accounts) - A.5.18 / A.8.2 | All user and privileged accounts | 6 accounts | All privileged accounts plus a selection of standard accounts | Access appropriate, but no periodic-review evidence (NC-3)
SA02 | Code changes / pull requests - A.8.25 | Releases during the period | 5 recent pull requests | Most recent production releases | Peer review performed; branch protection enforced. Conforming
SA03 | Training completion - A.6.3 | All 6 staff | All 6 (full check) | Small team; full population checked | Training delivered; completion not formally logged (OFI-2)
SA04 | Backup and restore tests - A.8.13 | Monthly backup tests | Last 3 months | Most recent months | Backups completed and restores tested. Conforming
SA05 | Risk register entries - 6.1.3 | 5 identified risks | All 5 | Small population; full check | Treatment recorded; R005 in progress. Conforming