## Corrective Action Plan
STARK INDUSTRIES INC. - Corrective Action Plan and Verification
ISO/IEC 27001:2022 Internal Audit - Stage 09. Corrective actions for nonconformities, with auditor verification and closure.
Audit: 16-20 Mar 2026 ¦ Lead Auditor: Nirmay Soni ¦ Version 1.0 ¦ Classification: Internal
Ref | Nonconformity | Clause / Control | Root Cause | Corrective Action (Plan) | Owner | Target Date | Action Taken / Evidence | Auditor Verification | Effectiveness | Closure Status | Closure Date
NC-1 | Legal and regulatory requirements not formally identified | Clause 4.2 / A.5.31 | ISMS documentation was based on a template that stated no legal requirements apply; the US SaaS legal context was never formally analysed. | Carry out a legal and regulatory analysis and create a Legal Requirements Register; correct the Scope and Information Security Policy statements. | Happy Hogan | 30 Apr 2026 | Legal Requirements Register v1.0 created (CAN-SPAM, applicable US state privacy laws, contractual obligations); Scope and InfoSec Policy updated. | Verified the register exists and covers the applicable requirements; confirmed the scope and policy statements were corrected. | Effective | Closed | 28 Apr 2026
NC-2 | Segregation of duties not formally addressed | A.5.3 | Small team size led to overlapping duties; segregation was managed informally without documentation. | Document a segregation-of-duties conflict matrix for the team and the compensating controls applied. | Happy Hogan | 15 May 2026 | Segregation-of-duties matrix documented; compensating controls recorded (peer review, management oversight, logging). | Verified the matrix and compensating controls are documented and communicated. | Effective | Closed | 12 May 2026
NC-3 | Periodic access reviews not evidenced | A.5.18 / A.8.2 | Access-review responsibility was defined in policy, but no schedule or record-keeping mechanism existed. | Establish a quarterly access-review schedule and perform the first review, retaining records. | Maria Hill | 30 Apr 2026 | Quarterly access-review schedule established; first review completed on 25 Apr 2026 with records retained, including privileged access. | Verified the first access review was completed and recorded and that a recurring schedule is in place. | Effective | Closed | 25 Apr 2026

## OFI Follow-Up
STARK INDUSTRIES INC. - Opportunity for Improvement Follow-Up
ISO/IEC 27001:2022 Internal Audit - Stage 09. Status of the opportunities for improvement (recommendations).
Audit: 16-20 Mar 2026 ¦ Lead Auditor: Nirmay Soni ¦ Version 1.0 ¦ Classification: Internal
Ref | Opportunity for Improvement | Control | Owner | Action Taken | Target Date | Status
OFI-1 | Single-cloud (AWS) dependency with no documented exit plan | A.5.30 | Maria Hill | Recommendation accepted; a cloud continuity and exit plan is being drafted to address prolonged AWS unavailability. | 31 May 2026 | In Progress
OFI-2 | Training-completion tracking is informal | A.6.3 | Happy Hogan | A central training-completion log has been introduced to evidence coverage across all staff. | 30 Apr 2026 | Implemented