## Audit Schedule
STARK INDUSTRIES INC. - Audit Schedule
ISO/IEC 27001:2022 Internal Audit - Stage 02. Session-by-session timetable for the fieldwork week.
Audit dates: 16 - 20 Mar 2026 ¦ Lead Auditor: Nirmay Soni ¦ Version 1.0 ¦ Classification: Internal
Session | Date | Time | Area / Clause | Topic | Auditee(s) | Auditor | Method
Opening | 16 Mar 2026 | 09:00 - 09:30 | All | Opening meeting | All auditees | Nirmay Soni | Meeting
S1 | 16 Mar 2026 | 09:30 - 11:00 | Clause 4 & 5 | Context, scope, leadership, policy, roles | Happy Hogan, Tony Stark | Nirmay Soni | Interview, Document review
S2 | 16 Mar 2026 | 11:15 - 13:00 | Clause 6 | Risk assessment, risk treatment, objectives | Happy Hogan, Nirmay Soni | Nirmay Soni | Document review, Interview
S3 | 17 Mar 2026 | 09:30 - 11:00 | Clause 7 | Competence, awareness, communication, documents | Happy Hogan | Nirmay Soni | Document review, Sampling
S4 | 17 Mar 2026 | 11:15 - 13:00 | Clause 8 / Annex A Tech | Operations, secure development | Natalia Romanoff, Maria Hill | Nirmay Soni | Interview, Observation
S5 | 18 Mar 2026 | 09:30 - 11:30 | Annex A Tech | Access control, cryptography, logging, monitoring | Maria Hill, James Rhodes | Nirmay Soni | Observation, Control testing, Sampling
S6 | 18 Mar 2026 | 11:45 - 13:00 | Annex A Org/People | Policies, supplier management, HR security | Happy Hogan | Nirmay Soni | Document review, Interview
S7 | 19 Mar 2026 | 09:30 - 11:00 | Annex A Physical / AWS | Physical and infrastructure (shared responsibility) | Maria Hill | Nirmay Soni | Document review, Interview
S8 | 19 Mar 2026 | 11:15 - 13:00 | Clause 9 & 10 | Monitoring, internal audit, mgmt review, improvement | Happy Hogan, James Rhodes | Nirmay Soni | Document review, Interview
Review | 19 Mar 2026 | 14:00 - 16:00 | All | Auditor review and findings consolidation | - | Nirmay Soni | Analysis
Closing | 20 Mar 2026 | 10:00 - 11:00 | All | Closing meeting and presentation of findings | All auditees | Nirmay Soni | Meeting